## Sheet1
| B | C | D | E |  | F | H
| Evans Invoices Itemized | as of | Friday 9/30/2022
| Line Item | Invoice Charge | Image Set | Complete Work from McCarty Specs | Repair Damages by McCarty |  | Note
| Sub-Totals | 41928.13 |  | 27095 | 14833 |  |  | 41928
1 | Invoice #1 6/22/2022 $11,750
2 | Repaired wall framing by sunroom | 250 |  |  | 250
3 | Repaired holes in wall cut by electrician | 750 |  |  | 750
4 | Excavated plumbing lines, cut up sections of concrete; | 1500 |  |  | 1500
5 | Removed all concrete that was cut up and concrete debris
6 | And trash and a several yards of mixed dirt
7 | Refinished walls completely | 6900 |  |  | 6900
8 | Removed archway and cut back wall, repaired framing and drywall | 600 |  |  | 600
9 | Removed door in hall and repaired drywall | 200 |  | 200
10 | Removed linoleum in laundry area and disposed | 150 |  | 150
11 | Repaired framing and drywall around 6 foot closet door | 200 |  |  | 200
12 | Deposit for plumbing | 1200 |  | 1200
13
14 | Invoice #2 7/10/2022 $6,200
15 | Backfilled concrete aggregate layer with 4 inches of crush and run stone
16 | Tamped backfill
17 | Installed vapor barrier where it was removed, sealed existing vapor barrier
18 | as necessary with spray foam.
19 | Drilled concrete and installed concrete pins set into expandable sealant.
20 | 8 inch on center staggered, installed rebar as needed for proper reinforcement
21 | Poured 5 yards of high strength concrete. | 2200 |  | 2200
22
23 | Deposit for paint, all walls in building prepped and installed
24 | one coat of primer sealer. All windows and doors and cabinets
25 | prepped with tape and plastic for painting | 2000 |  | 2000
26
27 | Deposit on for cabinet installation | 2000 |  | 2000
28
29 | Invoice #3 7/20/2022 $7,100
30 | Installed cabinets in kitchen.
31 | Checked existing partially installed cabinets for level and correct installation.
32 | Found entire cabinet structure to be out of level, it appears to have been installed from
33 | The low end of the slab which created an out of rack condition, seven cabinet parts were removed
34 | Completely, two large double boxes, two large end partitons next to the refrigerator
35 | Were 1 inch out of level within 6 ft., Two filler strips were removed also.
36 | Two other cabinets were adjusted on wall.
37 | Another 8 boxes were assembled to form the island area.
38 | The stove area was installed , 5 more boxes
39 | Adjusted doors cleaned cabinets and installed shelving.
40 | In the laundry existing used cabinets were installed on wall and base.
41 | And 4 cabinets boxes were custom modified to create a bench area 2 feet high | 8800 |  | 6600 | 2200
42
43 | Install stain grade birch plywood top on bench area with a wood veneer
44 | Edge cap. Sand and prep for paint or stain | 300 |  | 300
45
46 | Invoice #4 7/27/2022 $8,428
47 | Prepped floor, filled holes, cracks and leveled floor with planipatch floor repair
48 | Installed laminate flooring | 2900 |  | 1450 | 1450
49
50 | Install base molding and shoe molding | 850 |  | 850
51 | Baseboard and shoe molding | 735 |  | 735
52
53 | Balance of painting cost 5100 minus 2000.00 deposit | 3100 |  | 3100
54
55 | A/C repair Replaced one faulty low run capacitor,
56 | Found low freon and topped off unit
57 | Cleaned coil | 383.13 |  | 200 | 183
58
59 | Removed door casing in laundry room , 2 doors
60 | Found re entry door incorrectly installed
61 | Reset door, repaired drywall to create a flush look
62 | With no trim | 460 |  | 460
63
64 | Invoice #5 7/27/2022 approx $6,450 (pending)
65 | Install appliances removed all trash from the job | 900 |  | 900
66 | Backsplash install | 1550 |  | 1550
67 | Install barn doors | 1700 |  | 1700
68 | Repair window leak | 500 |  | 500
69 | Install stove hood | 150 |  | 150
70 | Have a gasfitter install gas valve and inspect lines | 300 |  | 300
71 | Run a new duct in attic for vent hood | 150 |  | 150
72 | Construction house cleaning, including windows and blinds | 1200 |  | 400 | 800
Additional Damages
Cabinets
Fans
Light
Loss of Use 4/15/2022 to 10/15/2022, 6 months:
Payments to Ian McCarty:
11/12/2021, Check #779, $13,000
2/12/2022, Check # 782, $20,000