| t\_ian.docx REVERSE CHRONOLOGICAL Page | | | |
| --- | --- | --- | --- |
| Day | Date |  |  |
|  |  |  |  |
| Tu | 5/11/2022 | Email from Meredith, no longer works for Ian. |  |
| Tu | 5/11/2022 | Site visit, took photos and videos. Trailer in driveway, taped CEASE and DESIST letter. (Met w Lloyd Evans). |  |
| M | 5/10 | Prelim conversation w attorney at Baird. |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| Tu | 4/26/2022 | Activity |  |
| M | 4/25/2022 | Activity, truck |  |
| Sa | 4/23/2022 | Send Ian email requesting phone call or on-site visit. No reply.  Visit Lewes to complete colors. Pantry without electric outlet.  Minimal changes, some drywall, sledge hammer for slab  Trailer parked on driveway, on grass |  |
| Tu | 4/ /2022 | Send Meredith and Ian email |  |
|  |  |  |  |
| Su | 4/10/2022 | Visit Lewes to select colors, match to cabinets, tile and flooring. Photos taken   1. Pantry without electric outlet 2. slab cutouts for electic not done 3. Demolition not complete--house filled with trash piles (not dumpster), laundry room floor not removed. 4. some drywall done 5. oven may not fit cabinet 6. heat set to 70 (last worker there on Thursday 4/7 7. Hood vent not yet cut |  |
| Thurs | 4/7 | Activity from |  |
| Wed | 4/6/2022 4:45pm | Call from Meredith (and text to Patti with same info)   1. Guys will be there today till 5-8:30 2. All demo work complete 3. Finishing studding, packing and drywall 4. "Cabinets are correct and staged to be installed tomorrow". 5. Drywall will be done by Monday 6. Cabinets are OK and complete 7. Electric status unknown 8. Floor and trim next week 9. Needs paint colors by next week 10. Haley at BKT on standby for granite templates   Based on garage log and video camera, guys actually there from 3:30 to 6:31, text sent to Meredith noting their end time. |  |
| Tues | 4/5/2022 | Garage door log indicates activity between 5:04 and 6:31 pm |  |
| Sun | 4/3/2022 | Visit Lewes (with family). Photos taken.  Called Ian, left message asking about status. |  |
| Sat | 4/2/2022 | ? |  |
| Th | 3/31/2022 | Call from Meredith and Ian, 7 min. Ask Ian about gas hookup, blames staff. Our gas will be done by our gas company. Also review timeline. Ian says work will be done "one week late" ie 4/22. |  |
|  |  |  |  |
| W | 3/30/2022 | Patti checks Better Business Bureau reviews. Finds two reports of incorrect gas hookup, as well as "revoked" status on BBB. |  |
| M | 3/28/2022 7:48pm | Patti receives text from neighbor asking about taking in garbage cans, tipped over, left since Friday 3/25. |  |
|  |  |  |  |
| Fri | 3/18/2022 | **Meet w Ian and electrician** to review job. Ian does not remember extending wall for cooktop. Remind electrician about outlet in pantry. Also review switching, other wiring, light positions |  |
| Sat | 2/26/2022 | Visit Lewes. |  |
|  |  |  |  |
| Tu | 2/15/2022 | Some activity |  |
| M | 2/14/2022 | No activity |  |
| Sa | 2/12/2022 11 am | **Meet with Ian** to review job, provide check for $20,000?  Job to start on Monday 2/14/2022 |  |
|  |  |  |  |
|  | 11/\_\_/2021 | Sign final contract and addendum |  |