## Sheet1
| B | C | D | E |  | F | H
1 | Evans Invoices Itemized | as of | 9/14/2022
2 | Line Item | Invoice Charge | Image Set | Complete Work from McCarty Specs | Repair Damages by McCarty | Not Included in original scope | Note
| Sub-Totals |  |  | 4150 | 5600 | 843.13
1 | Invoice #1 6/22/2022 $11,750
2 | Repaired wall framing by sunroom | 250 |  |  | 250
3 | Repaired holes in wall cut by (prior) electrician | 750 |  |  | 750
4 | Excavated plumbing lines, cut up sections of concrete | 1500 |  |  | 1500
5 | Removed all concrete that was cut up and concrete debris | 6900 |  | 3900 | 3000
6 | And trash and a several yards of mixed dirt | 600
7 | Refinished walls completely |  |  | 100 | 100
8 | Removed archway and cut back wall, repaired framing and drywall |  |  | 150
9 | Removed door in hall and repaired drywall
Removed linoleum in laundry area and disposed
Repaired framing and drywall around 6 foot closet door
Deposit for plumbing
Deposit for plumbing
Invoice #2 7/10/2022 $6,200
Backfilled concrete aggregate layer with 4 inches of crush and run stone
Tamped backfill
Installed vapor barrier where it was removed, sealed existing vapor barrier
as necessary with spray foam.
Drilled concrete and installed concrete pins set into expandable sealant.
8 inch on center staggered, installed rebar as needed for proper reinforcement
Poured 5 yards of high strength concrete.
Deposit for paint, all walls in building prepped and installed
one coat of primer sealer. All windows and doors and cabinets
prepped with tape and plastic for painting
Deposit on for cabinet installation
Invoice #3 7/20/2022 $9,100
Installed cabinets in kitchen.
Checked existing partially installed cabinets for level and correct installation.
Found entire cabinet structure to be out of level, it appears to have been installed from
The low end of the slab which created an out of rack condition, seven cabinet parts were removed
Completely, two large double boxes, two large end partitons next to the refrigerator
Were 1 inch out of level within 6 ft., Two filler strips were removed also.
Two other cabinets were adjusted on wall.
Another 8 boxes were assembled to form the island area.
The stove area was installed , 5 more boxes
Adjusted doors cleaned cabinets and installed shelving.
In the laundry existing used cabinets were installed on wall and base.
And 4 cabinets boxes were custom modified to create a bench area 2 feet high
Install stain grade birch plywood top on bench area with a wood veneer
| Edge cap. Sand and prep for paint or stain | 9100
Invoice #4 7/27/2022 $8,428
Prepped floor, filled holes, cracks and leveled floor with planipatch floor repair
Installed laminate flooring
Install base molding and shoe molding
Baseboard and shoe molding
Balance of painting cost 5100 minus 2000.00 deposit
A/C repair Replaced one faulty low run capacitor,
Found low freon and topped off unit
| Cleaned coil | 383.13 |  |  |  | 383.13
Removed door casing in laundry room , 2 doors
Found re entry door incorrectly installed
Reset door, repaired drywall to create a flush look
| With no trim |  |  |  |  | 460
Invoice #5 7/27/2022 $6,450 (pending)
Install appliances removed all trash from the job
Backsplash install
Install barn doors
Repair window leak
Install stove hood
Have a gasfitter install gas valve and inspect lines
Run a new duct in attic for vent hood
Construction house cleaning, including windows and blinds